## Sheet1
Account Name
Prosess Name:
Developer Name:
Tasks | Estimation (Day) | Notes
Solution design and architecture | 1
Extracting data from invoices (story) | 1
Validating extracted data (story) | 1
Entering data into accounting system (story) | 2
Creating process output report and sending e-mail to process owner (story) | 0.5
Unit Tests, Best Practices | 0.8 | 0.2 * 4 User Story = 0.8
Integration, Functional Tests | 0.5
Code review | 0.5
User acceptance testing (UAT), Deploy | 1
(All - Code Review) + Contingency additional time (%30) | 10.14
Total Dev Effort (All - Code Review) | 7.8
For more information:
https://github.com/seymenbahtiyar/RPA_Development_Effort_Estimation/blob/main/README.md